## Slide 1
ENTERPRISE RISK ASSESSMENT
Amazon’s Proposed Acquisition of an AI-Powered Last-Mile Delivery Optimization Platform (RIVR)
ALY 6130 – Risk Management Analytics | Northeastern University | Instructor: Abeba Nigussie Turi
Group 6: Sandra Amponsah | Truc Linh Hoang | Victoria Kpetigo
June 26, 2026

## Slide 2
PRESENTATION AGENDA
What This Assessment Covers
01
Background & Strategic Context
Amazon’s last-mile challenge and the competitive landscape
02
Risk Identification
A 32-risk register and three priority risks carried to analysis
03
Qualitative Assessment
Scenario Analytics and Industry Fusion Analytics
04
Quantitative Assessment
I&W analysis, Monte Carlo simulation, ML prediction
05
Risk Response & KRIs
Treatment strategies, trigger points, monitoring
06
Conclusion & Recommendations
Net portfolio value and non-negotiable conditions
2

## Slide 3
01 - BACKGROUND & STRATEGIC CONTEXT
The Business Case for AI in the Last Mile
8M+
packages / day
at $14–$17 each
50–60%
of parcel cost
is the last mile (BCG, 2026)
10–25%
cost reduction
achievable via AI routing
$50.2B
EU AI Act exposure
7% of $716.9B FY2025 revenue
Competitive urgency - the benchmark Amazon must surpass
UPS ORION (since 2012) $300–400M/yr savings · 100M fewer miles/yr · 14 years to build
FedEx Surround (since 2019) ~15M shipments/day with real-time AI
Oracle / SAP TM (20+ years) Enterprise ERP lock-in · $5M–$30M switching cost per client
Walmart AI (since 2020) 30% shipping-cost reduction achieved at scale
3

## Slide 4
02 - UNIFIED PROBLEM & IMPACT STATEMENT
A Single, Enterprise-Wide Challenge
PROBLEM STATEMENT
Amazon’s last-mile network faces compounding, interconnected risks - financial overpayment, operational disruption, competitive displacement, cybersecurity breach, algorithmic bias, low user adoption, vendor lock-in, and regulatory non-compliance - that cannot be managed without a comprehensive ERM framework governing every phase of the platform’s acquisition, integration, and operation. Left unmanaged, they erode acquisition ROI, weaken Amazon’s competitive position, and expose the company to CCPA, EU AI Act, and antitrust enforcement.
QUANTIFIED IMPACT
$400M–$1.36B / yr unrealized savings if efficiency is not captured
$10.22M average US data-breach cost (IBM, 2025)
~$50.2B EU AI Act exposure - 7% of FY2025 revenue
$7,500 / violation CCPA, across 200M+ Prime customers
4

## Slide 5
02 - IDENTIFICATION OF RISKS
Consolidated Risk Register — 32-Risk Severity Heat Map
All 32 negative risks plotted on a Likelihood (1/3/5/7/9) × Impact (1/2/4/6/8/9) grid. Each cell’s score is L × Impact; color marks its severity tier.
IMPACT (I)
9 Extreme
$5B+
8 Very High
$500M–5B
6 High
$100M–500M
4 Moderate
$10M–100M
2 Low
$1M–10M
1 Very Low
<$1M
9
27
45
R10 R14
63
R7
81
8
24
R12
40
R11 R19 R28
R29
56
R1 R5 R22
R27
72
R26
6
18
R13 R32
30
R3 R6 R8
R9 R15 R17
R20 R30 R31
42
R2 R16 R18
R23 R24
54
R25
4
12
20
R21
28
R4
36
2
6
10
14
18
1
3
5
7
9
1
Very Unlikely
3
Somewhat Unlikely
5
50–50
7
Somewhat Likely
9
Very Likely
LIKELIHOOD (L)
Summary
Score = Likelihood × Impact. Cells run green → red as severity rises; the number in each cell is its risk score (max 81).
Where the risk sits
7 Very High · 11 High · 14 Moderate · 0 Low. The portfolio clusters in the upper-middle of the grid — high-consequence, mid-likelihood — not in the extreme tails.
Highest-severity cells
R7 (peak-operations downtime) and R26 (cost of lagging in AI adoption) occupy the top severity cells — the register’s most urgent exposures.
Link to the analysis
The three priority risks (PR1–PR3) on the next slide are drawn from this register. Four opportunities are tracked in a separate register and are not plotted here.
5

## Slide 6
02 - IDENTIFICATION OF RISKS
Three Priority Risks Carried to Analysis
From a consolidated 32-risk register (7 categories) and a separate 4-opportunity register, three risks were selected for deep quantitative analysis. Labeled PR1–PR3 to avoid clashing with register IDs.
THREAT
PR1 Commercial Market-Entry / Win-Rate
7 × 6 = 42 (HIGH)
Amazon enters the commercial logistics-software market without a sales-engineering or SLA capability
→ incumbents (ORION, Surround, Oracle, SAP) leverage lock-in
→ win-rate < 40%
→ acquisition ROI erodes.
Edge at stake: the platform’s data from 8M daily stops cannot be sold without enterprise sales capability.
THREAT - HIGHEST TAIL
PR2 Cybersecurity Breach - Geo/Address Data
5 × 9 = 45 (HIGH)
A new attack surface - driver geolocation, customer addresses, delivery photos
→ zero-trust not deployed before integration
→ ransomware / unauthorized API access
→ CCPA notification + disruption.
Edge at stake: a breach turns Amazon’s data-density advantage into a multi-jurisdiction liability.
OPPORTUNITY
PR3 Cost-Reduction & Sustainability
9 × 8 = 72 (HIGH UPSIDE)
AI optimization across 8M daily packages → 15–25% per-package reduction
→ $400M–$1.36B savings + CO₂ cuts
→ pre-compliance with Clean Miles becomes a competitive moat.
Edge enabled: every year of delay forfeits another year of ORION’s compounding $400M advantage.
6

## Slide 7
03 - QUALITATIVE RISK ASSESSMENT
Scenario Analytics & Industry Fusion Analytics
Methods from Fleisher & Bensoussan (2015): Scenario Analytics (Ch. 22) and Industry Fusion Analytics (Ch. 17).
Risk | Base-case scenario | Industry-fusion benchmark | Proceed?
PR1 | Win-rate settles near 38% for three quarters; positive internal ROI but missed external targets. | Oracle–PeopleSoft (36-mo ramp); Google Cloud (<30% win-rate for 3 yrs despite better tech). | Yes
PR2 | Months 6–9 are peak exposure; attack detected via geo-API anomaly before exfiltration. | IBM 2025 ($10.22M US avg); 33% logistics AWS credentials exposed; Colonial Pipeline ($4B+). | Yes
PR3 | Adoption ~70% in 12 months; ~14% per-package reduction ≈ $490M/yr. | UPS ORION ($300–400M/yr); Walmart (30%); Shuaibu et al. (15–25%). | Yes
Key insight: the commercial maturity of the logistics-software market - not the technology - is the primary source of PR1 risk.
7

## Slide 8
04 - QUANTITATIVE RISK ASSESSMENT
I&W Analysis · Monte Carlo · ML Prediction (50,000 trials)
PR1 Market-Entry
I&W P = 0.65
EMV −$368M
P95 downside $890M
Signal: sales-eng vacancy gap
ML AUC 0.87
Mitigate → residual −$239M (−35%)
PR2 Cyber Breach
I&W P = 0.47
EMV −$231M
P95 downside $701M
Signal: anomalous geo-API traffic
ML AUC 0.89
Mitigate + Transfer → −$104M (−55%)
PR3 Cost Reduction
I&W P = 0.62
EMV +$453M
P95 upside +$991M
Signal: driver AI-route adoption
ML AUC 1.00
Exploit + Enhance → +$534M (+18%)
8

## Slide 9
04 - MONTE CARLO SIMULATION
Full Exposure Distributions (50,000 Trials)
Each trial draws a probability (Beta) and a conditional impact (PERT). The spread - not just the mean - is what justifies sizing contingency reserves against the P95 tail rather than the average.
Figure 1. Panels labeled R1–R3 as in the notebook (PR1–PR3 here). Gold line = expected impact; dashed line = P95 (downside for PR1/PR2, upside for PR3).
9

## Slide 10
05 - RISK RESPONSE STRATEGY
Treatment Aligned to Internal & External Environment
PR1 | MITIGATE
Pre-launch benchmarking vs ORION/Surround; close top feature gaps
Hire 15–20 enterprise sales engineers before the first RFP
Tiered introductory pricing within FTC conduct limits
Win-rate dashboard; pause commercialization if < 40% for 2 quarters
Env: FTC antitrust trial (Oct 2026) limits pricing freedom.
PR2 | MITIGATE + TRANSFER
Zero-trust as a hard launch gate - before any live data
API gateway with anomaly detection; CISO escalation in 15 min
Logistics cyber insurance up to $50M / incident
Tested delivery-data incident-response playbook
Env: CCPA $7,500/violation × 200M+ customers sizes the insurance floor.
PR3 | EXPLOIT + ENHANCE
Scale from 3-city pilot to 50+ stations in 18 months
Driver-adoption program → 80% per market within 6 months
Pre-comply with California Clean Miles before deadline
Public CO₂ KPI anchored to ORION’s 100M-miles benchmark
Env: Clean Miles + EU urban-access mandates create an access moat.
10

## Slide 11
05 - KEY RISK INDICATORS & TRIGGER POINTS
Monitoring Framework (CRISP-DM Aligned)
Every KRI gives 30–90 days of advance warning and draws on the dominant ML signal for its risk; each red trigger is benchmark-anchored (see next slide).
Risk | KRI metric | Green | Amber | Red - trigger & response | Freq.
PR1 | Enterprise win-rate vs ORION/Surround | ≥ 50% | 40–49% | < 40% for 2 quarters → pause commercialization + VP review | Qtrly
PR1 | Sales-engineering headcount vs target | ≥ 90% | 75–89% | < 75% → emergency recruiting + CEO escalation | Monthly
PR2 | Critical vulns past 15-day SLA | Zero | 1–2 near limit | Any vuln > 15 days → patch sprint + board notice | Weekly
PR2 | Anomalous geo-API / unauthorized access | Zero | Elevated volume | Any confirmed access → API lockdown + CCPA 72h clock | Cont.
PR3 | Per-package cost reduction vs baseline | ≥ 15% | 5–14% | < 5% → suspend expansion + model audit | Monthly
PR3 | Driver adoption of AI routes | ≥ 80% | 60–79% | < 60% (or < 80% after 6 mo) → DSP review + incentives | Monthly
11

## Slide 12
04 - QUANTITATIVE RISK ASSESSMENT
Warning-Threshold Calibration — Benchmark Basis
In response to feedback that thresholds appeared generic, every red trigger is anchored to a published logistics, sales, or cybersecurity benchmark rather than set by convention.
Threshold | Where used | Benchmark basis (why this cut-off) | Source
Composite ≥ 0.55 → Red | Master escalation trigger (all three priority risks) | Maps to the High–Very-High band of the register (40/81 ≈ 0.49; 54/81 ≈ 0.67) — fires where the firm already requires active executive mitigation. | ISO 31000:2018; COSO ERM (2017)
PR1: win-rate < 40% for two quarters → Red | win-rate-gap indicator | Competitive B2B win-rates average ≈ 47% (RAIN Group) and ≈ 21% blended (HubSpot); sub-40% versus ORION / Surround means losing most head-to-head bake-offs. | RAIN Group (2023); HubSpot (2024)
PR2: critical vuln open > 15 days → Red | vulns-past-SLA indicator | CISA BOD 19-02 sets a 15-day remediation deadline for critical vulnerabilities on internet-facing systems; reinforced by IBM’s 241-day mean breach lifecycle. | CISA BOD 19-02; IBM (2025)
PR3: cost reduction < 5% → opportunity not materializing | cost-reduction indicator | Documented AI route-optimization savings run 15–30%; the conservative INFORMS / ORION floor is ≈ 5%. Below 5% the platform underperforms the weakest benchmark and the value thesis fails. | INFORMS / ORION; Shuaibu et al. (2025)
Bottom line: each warning level is benchmark-derived, so a red state marks an exposure external evidence already treats as unacceptable.
12

## Slide 13
06 - CONCLUSION & RECOMMENDATIONS
Proceed - Under an Active ERM Program
NET PORTFOLIO VALUE AFTER TREATMENT
+$191M
−$239M (PR1) −$104M (PR2) +$534M (PR3), before strategic option value
THREE NON-NEGOTIABLE CONDITIONS
01
Zero-trust before any live customer-data integration
02
Pre-launch sales-engineering team of ≥ 15 FTEs
03
80% driver-adoption target per market, monitored monthly
SUMMARY FINDINGS
PR2 carries the highest tail ($701M P95) despite moderate probability - zero-trust is a launch gate, not an IT project.
PR1’s $368M EMV is addressable by closing the sales-engineering gap before launch - the model’s top-priority action.
PR3 offers a +$453M to +$991M upside that erodes by ~$400M for every year of delay against ORION.
Regulatory inputs (EU AI Act, CCPA, Clean Miles) are model inputs, not background - they calibrate the distributions directly.
13

## Slide 14
REFERENCES
Sources
Amazon.com, Inc. (2025). Form 10-K, FY2024. U.S. SEC.
BCG. (2026). Last-mile delivery accounts for 50–60% of total parcel costs.
California Attorney General. (2023). California Consumer Privacy Act (CCPA).
CCJ Digital. (2026). Supply chain cyber threats: malicious AI and logistics data.
COSO. (2017). Enterprise risk management-Integrating with strategy and performance.
Cybersecurity and Infrastructure Security Agency. (2019). Binding Operational Directive 19-02: Vulnerability remediation requirements for internet-accessible systems.
Deep Tech Nation Switzerland. (2026). Amazon acquires RIVR: An ETH Zurich robotics spinout.
European Parliament. (2024). Regulation (EU) 2024/1689 (EU AI Act).
FedEx Corporation. (2024). FedEx Surround platform overview.
Federal Trade Commission. (2023). FTC v. Amazon.com, Inc.
Financial Content. (2026). Amazon (AMZN) 2026 analysis: The $200B AI and aerospace pivot.
Fleisher, C. S., & Bensoussan, B. E. (2015). Business and competitive analysis (2nd ed.). FT Press.
HubSpot. (2024). 2024 sales trends report. HubSpot, Inc.
IBM Security. (2025). Cost of a data breach report 2025.
INFORMS. (2016). UPS ORION - Franz Edelman Award.
ISO. (2018). ISO 31000:2018 Risk management-Guidelines.
NIST. (2023). AI Risk Management Framework (AI RMF 1.0).
Oracle (2024); SAP SE (2024). Logistics / Transportation Management platform overviews.
RAIN Group. (2023). Win rate benchmarks: Top-performing sales organizations.
Shuaibu, A. S., Mahmoud, A. S., & Sheltami, T. R. (2025). A review of last-mile delivery optimization. Drones, 9(3), 158.
Skadden. (2025). M&A in the AI era: antitrust and national-security considerations.
Statista. (2024). Last-mile share of total shipping costs, 2018–2023.
Walmart Inc. (2024). Form 10-K - AI supply-chain transformation.
14